## Foglio1 (2)
298577
[13 empty] | External Costs |  |  | Internal Costs
[13 empty] | 263097 |  |  | 35480
TOT |  |  |  | tot | WBS | tot | d | Task | Time [days] | Task Cost | Parents | Comments | Materials | External Enginering | Supplier | Manpower 3 people [50€/h] | Internal Engineering 2 people [70€/h]
[13 empty] | 21500 | 105997 | 135600 | 28200 | 7280
298577 | Engineering | 112157 | Process | 41158 | Chemical Process | 15000 | 18 | PFD - Heat&Mass Balance | 13 | 2500 |  |  | 0 | 2500 | 0 | 0 | 0
| Engineering | [6 empty] | Filter Data Sheet | 1 | 2500 | PFD - Heat&Mass Balance |  | 0 | 2500 | 0 | 0 | 0
| Engineering | [6 empty] | Pump Data Sheet | 1 | 2500 | PFD - Heat&Mass Balance |  | 0 | 2500 | 0 | 0 | 0
| Engineering | [6 empty] | Sterilizer&mineralizer DS | 1 | 2500 | PFD - Heat&Mass Balance |  | 0 | 2500 | 0 | 0 | 0
| Engineering | [6 empty] | Valve Data Sheet | 1 | 2500 | PFD - Heat&Mass Balance, Valve List |  | 0 | 2500 | 0 | 0 | 0
| Engineering | [6 empty] | Instrument Data Sheet | 1 | 2500 | PFD - Heat&Mass Balance, Instruments List |  | 0 | 2500 | 0 | 0 | 0
| Engineering |  |  |  | Automation Logic | 19998 | 10 | Logic Map | 5 | 6666 | PFD - Heat&Mass Balance, P&ID |  | 0 | 6666 | 0 | 0 | 0
| Engineering | [6 empty] | Instruments List | 2 | 6666 | P&ID |  | 0 | 6666 | 0 | 0 | 0
| Engineering | [6 empty] | Pneumatic Calculation | 3 | 6666 | Instruments List |  | 0 | 6666 | 0 | 0 | 0
| Engineering |  |  |  | Mechanical Process | 6160 | 11 | Piping Class | 2 | 1120 | PFD - Heat&Mass Balance |  | 0 | 0 | 0 | 0 | 1120
| Engineering | [6 empty] | Painting Procedure | 2 | 1120 | PFD - Heat&Mass Balance |  | 0 | 0 | 0 | 0 | 1120
| Engineering | [6 empty] | Valve List | 2 | 1120 | P&ID |  | 0 | 0 | 0 | 0 | 1120
| Engineering | [6 empty] | P&ID | 5 | 2800 | PFD - Heat&Mass Balance, Piping Class |  | 0 | 0 | 0 | 0 | 2800
| Engineering |  | Mechanical | 30000 | BOM | 6000 | 2 | BOM BOP | 2 | 6000 | 3D Model |  | 0 | 6000 | 0 | 0 | 0
| Engineering |  |  |  | Technical Drawing | 18000 | 9 | General Arrangement | 1 | 6000 | 3D Model |  | 0 | 6000 | 0 | 0 | 0
| Engineering | [6 empty] | Isometric DWG | 5 | 6000 | General Arrangement, Piping Class |  | 0 | 6000 | 0 | 0 | 0
| Engineering | [6 empty] | Structures DWG | 3 | 6000 | General Arrangement |  | 0 | 6000 | 0 | 0 | 0
| Engineering |  |  |  | 3D Model | 6000 | 20 | 3D Model | 20 | 6000 | P&ID | a 10g prima -> GA preliminare, a 12 prima -> BOM preliminare. una volta concluso £D model, avremo GA Finale e BOM definitiva Approvati. Ricordiamo che c'è da considerare ricezione MEchanical dwg dai vari procurement (sopratutto equipment, le valvole hanno scartamenti standard, ma per ingombri, soprattutto le attuate, si dovrebbero avere i dsegni tecnici) | 0 | 6000 | 0 | 0 | 0
| Engineering |  | Automation | 40999 | Flowcomputer Logic | 16000 | 35 | Control Panel Logic | 25 | 8000 | Logic Map |  | 0 | 8000 | 0 | 0 | 0
| Engineering | [6 empty] | Control Systems | 10 | 8000 | Logic Map | -> Control Panel FAT, Automation final test, IECEx Detailed Test, Assembled Skid FAT | 0 | 8000 | 0 | 0 | 0
| Engineering |  |  |  | Electrical&Pneumatic | 24999 | 45 | Electrical Hook-Up | 25 | 8333 | Control Panel Logic | -> E&I installation, Automation Test, IECEx Test | 0 | 8333 | 0 | 0 | 0
| Engineering | [6 empty] | Wiring Diagram | 10 | 8333 | Control Panel Logic | - cable & cabletray installation, JBs installation, FAT control Panel | 0 | 8333 | 0 | 0 | 0
| Engineering | [6 empty] | Pneumatic Hook-up | 10 | 8333 | Pneumatic Calculation | -> E&I installation, Mechanical Erection(Actuated, ESD Valves), tubing Construction, FAT Assembled Skid | 0 | 8333 | 0 | 0 | 0
| Procurement | 90200 | Critical Components | 21000 | Filter | 6000 | 140 | Filter Procurement | 140 | 6000 | Filter Data Sheet |  | 0 | 0 | 6000 | 0 | 0
| Procurement |  |  |  | Sterilizer&mineralizer | 7000 | 150 | Sterilizer&mineralizer Procurement | 150 | 7000 | Sterilizer&mineralizer DS |  | 0 | 0 | 7000 | 0 | 0
| Procurement |  |  |  | Pump | 8000 | 150 | Pump Procurement | 150 | 8000 | Pump Data Sheet |  | 0 | 0 | 8000 | 0 | 0
| Procurement |  | Accessories | 69200 | Bulk Piping | 16500 | 110 | Fitting Procurement | 30 | 10000 | BOM BOP |  | 10000 | 0 | 0 | 0 | 0
| Procurement | [6 empty] | Flanges Procurement | 40 | 4000 | BOM BOP |  | 4000 | 0 | 0 | 0 | 0
| Procurement | [6 empty] | Gaskets Procurement | 25 | 1500 | BOM BOP |  | 1500 | 0 | 0 | 0 | 0
| Procurement | [6 empty] | Stud&Nuts Procurement | 15 | 1000 | BOM BOP |  | 1000 | 0 | 0 | 0 | 0
| Procurement |  |  |  | Valves | 21000 | 340 | Manual Valves Procurement | 90 | 3000 | Valve Data Sheet | -> mechanical Erection | 0 | 0 | 3000 | 0 | 0
| Procurement | [6 empty] | Actuated Valves Procurement | 120 | 10000 | Valve Data Sheet | -> mechanical Erection | 0 | 0 | 10000 | 0 | 0
| Procurement | [6 empty] | ESD valves Procurement | 130 | 8000 | Valve Data Sheet | -> mechanical Erection | 0 | 0 | 8000 | 0 | 0
| Procurement |  |  |  | flow computer | 12000 | 170 | Flow Computer Procurement | 170 | 12000 | Instrument Data Sheet | -> E&I Erection | 0 | 0 | 12000 | 0 | 0
| Procurement |  |  |  | instruments | 14700 | 240 | P/T Gauges Procurement | 25 | 900 | Instrument Data Sheet | -> E&I Erection | 0 | 0 | 900 | 0 | 0
| Procurement | [6 empty] | P/T Transimitters Procurement | 60 | 4000 | Instrument Data Sheet | -> E&I Erection | 0 | 0 | 4000 | 0 | 0
| Procurement | [6 empty] | Level Transmitter Procurement | 90 | 8000 | Instrument Data Sheet | -> E&I Erection | 0 | 0 | 8000 | 0 | 0
| Procurement | [6 empty] | Flow Orifices Procurement | 40 | 1300 | Instrument Data Sheet | -> E&I Erection | 0 | 0 | 1300 | 0 | 0
| Procurement | [6 empty] | JBs Procurement | 25 | 500 | Instrument Data Sheet | -> E&I Erection | 0 | 0 | 500 | 0 | 0
| Procurement |  |  |  | Steelworks | 5000 | 20 | Steelworks&support Material Construction | 20 | 5000 | BOM BOP | -> Structures Prefabbrication | 5000 | 0 | 0 | 0 | 0
| Construction | 78400 | Mechanical Prefabbrication | 47000 | Structures Prefabbrication | 2000 | 5 | Structures Prefabbrication Construction | 5 | 2000 | Structures DWG, Steelworks&support Material Construction | -> NDT on weldings structure | 0 | 0 | 0 | 2000 | 0
| Construction |  |  |  | Painting Structures | 7000 | 10 | Painting Structures Construction | 10 | 7000 | Painting Procedure, Dimensional Check (Observer) | -> painting check structures | 0 | 0 | 7000 | 0 | 0
| Construction |  |  |  | Piping Prefabbrication | 14000 | 35 | Piping Prefabbrication Construction | 35 | 14000 | Isometric DWG, Fitting Procurement, Flanges Procurement, Gaskets Procurement, Stud&Nuts Procurement | -> NDT on wedings Piping | 0 | 0 |  | 14000 | 0
| Construction |  |  |  | Pickling | 3000 | 5 | Pickling | 5 | 3000 | Hydrostatic Pressure TEst | -> painting piping | 0 | 0 | 3000 | 0 | 0
| Construction |  |  |  | Painting Piping | 21000 | 15 | Painting Piping Construction | 15 | 21000 | Painting Procedure, Pickling | -> painting check piping | 0 | 0 | 21000 | 0 | 0
| Construction |  | Mechanical Erection | 4400 | Equipment | 400 | 1 | Equipment Construction | 1 | 400 | Pneumatic Hook-up, Painting Check (Sructure), ESD valves Procurement | -> E&I installation, FAT assembled Skdi | 0 | 0 | 0 | 400 | 0
| Construction |  |  |  | Piping | 2000 | 5 | Piping Construction | 5 | 2000 | Pneumatic Hook-up, Painting Check (Sructure), ESD valves Procurement |  | 0 | 0 | 0 | 2000 | 0
| Construction |  |  |  | Valves | 2000 | 5 | Valves Construction | 5 | 2000 | Pneumatic Hook-up, Painting Check (Sructure), ESD valves Procurement |  | 0 | 0 | 0 | 2000 | 0
| Construction |  | Electrical & Instrument Installation | 27000 | instruments | 27000 | 29 | instruments Construction | 5 | 5400 | Electrical Hook-Up, Valve List, Pneumatic Hook-up, Contol Panel FAT, Flow Computer Procurement, P/T Gauges Procurement, P/T Transimitters Procurement, Level Transmitter Procurement, Flow Orifices Procurement, JBs Procurement | ipotizzo 3/4 persone, -> IECEx Test, Automation TEst | 0 | 0 | 5400 | 0 | 0
| Construction |  |  |  | JBs |  |  | JBs Construction | 2 | 5400 | Electrical Hook-Up, Valve List, Pneumatic Hook-up, Contol Panel FAT, Flow Computer Procurement, P/T Gauges Procurement, P/T Transimitters Procurement, Level Transmitter Procurement, Flow Orifices Procurement, JBs Procurement |  | 0 | 0 | 5400 | 0 | 0
| Construction |  |  |  | cables & cabletray |  |  | cables & cabletray Construction | 10 | 5400 | Electrical Hook-Up, Valve List, Pneumatic Hook-up, Contol Panel FAT, Flow Computer Procurement, P/T Gauges Procurement, P/T Transimitters Procurement, Level Transmitter Procurement, Flow Orifices Procurement, JBs Procurement |  | 0 | 0 | 5400 | 0 | 0
| Construction |  |  |  | Actuated Valve Setup |  |  | Actuated Valve Setup Construction | 2 | 5400 | Electrical Hook-Up, Valve List, Pneumatic Hook-up, Contol Panel FAT, Flow Computer Procurement, P/T Gauges Procurement, P/T Transimitters Procurement, Level Transmitter Procurement, Flow Orifices Procurement, JBs Procurement |  | 0 | 0 | 5400 | 0 | 0
| Construction |  |  |  | tubing Construction |  |  | tubing Construction | 10 | 5400 | Electrical Hook-Up, Valve List, Pneumatic Hook-up, Contol Panel FAT, Flow Computer Procurement, P/T Gauges Procurement, P/T Transimitters Procurement, Level Transmitter Procurement, Flow Orifices Procurement, JBs Procurement |  | 0 | 0 | 5400 | 0 | 0
| Testing | 17820 | FATs Procedure | 2000 | Equipment FAT | 400 | 3 | Pump FAT | 1 | 400 | Pump Procurement | -> mechanical erection equipment | 0 | 0 | 0 | 400 | 0
| Testing |  |  |  |  | 400 |  | Sterilizer&Mineralizer FAT | 1 | 400 | Sterilizer&mineralizer Procurement |  | 0 | 0 | 0 | 400 | 0
| Testing |  |  |  |  | 400 |  | Filter FAT | 1 | 400 | Filter Procurement |  | 0 | 0 | 0 | 400 | 0
| Testing |  |  |  | Outside Skid FAT | 400 | 1 | Contol Panel FAT | 1 | 400 | Final Tests | -> E&I installation | 0 | 0 | 0 | 400 | 0
| Testing |  |  |  | Assembled Skid FAT | 400 | 1 | Assembled Skid FAT | 1 | 400 | Final Tests | -> ,Automation TEst, Final Test | 0 | 0 | 0 | 400 | 0
| Testing |  | Skid | 15820 | Structure | 1500 | 3 | NDT on Weldings (Structure) | 1 | 500 | Structures Prefabbrication Construction | -> dimensional check structures | 0 | 0 | 100 | 400 | 0
| Testing | [6 empty] | Dimensional Check | 1 | 500 | Final Tests | -Painting structure | 0 | 0 | 100 | 400 | 0
| Testing | [6 empty] | Painting Check (Sructure) | 1 | 500 | Painting Check (Sructure) | -> mechanical erection | 0 | 0 | 100 | 400 | 0
| Testing |  |  |  | Piping | 3000 | 6 | NDT on Weldings (Piping) | 1 | 600 | Piping Prefabbrication Construction | -> dimensional Check | 0 | 0 | 200 | 400 | 0
| Testing | [6 empty] | Dimensional Check | 1 | 600 | Final Tests | -> hydrostatic Pressure Test | 0 | 0 | 200 | 400 | 0
| Testing | [6 empty] | Hydrostatic Pressure TEst | 3 | 1400 | Dimensional Check | -> pickling | 0 | 0 | 200 | 1200 | 0
| Testing | [6 empty] | Painting Check (Piping) | 1 | 400 | Painting Piping Construction | -> Mechanical Erection | 0 | 0 | 0 | 400 | 0
| Testing |  |  |  | Observer (Third Party) | 8000 | 3 | Observer (Third Party) | 3 | 8000 | Final Tests | needed over some tests | 0 | 0 | 8000 | 0 | 0
| Testing |  |  |  | Assembled Skid | 3320 | 7.5 | Dimensional Check (Observer) | 0.5 | 200 | NDT on Weldings (Piping), NDT on Weldings (Structure), Dimensional Check (Observer) | questi sono in ordine e non uno dopo l'altro, quindi regolate di conseguenza con le altre relazioni precedenti | 0 | 0 | 0 | 200 | 0
| Testing | [6 empty] | IECEx Detailed Test | 3 | 1200 | Control Systems, Electrical Hook-Up, instruments Construction, Automation Test, tubing Construction, Dimensional Check (Observer), JBs Construction, cables & cabletray Construction |  | 0 | 0 | 0 | 1200 | 0
| Testing | [6 empty] | Automation Test | 1 | 400 | IECEx Detailed Test |  | 0 | 0 | 0 | 400 | 0
| Testing | [6 empty] | Final Tests | 1 | 400 | Automation Test, Assembled Skid FAT |  | 0 | 0 | 0 | 400 | 0
| Testing | [6 empty] | Documentation Pack | 2 | 1120 | Final Tests |  | 0 | 0 | 0 | 0 | 1120

## Foglio2
task name |  | duration | materials cost | ext engineering | supplier | manpower | internal engineerign
PFD - Heat&Mass Balance | Engineering | 13 | 0 | 2500 | 0 | 0 | 0
Filter Data Sheet | Engineering | 1 | 0 | 2500 | 0 | 0 | 0
Pump Data Sheet | Engineering | 1 | 0 | 2500 | 0 | 0 | 0
Sterilizer&mineralizer DS | Engineering | 1 | 0 | 2500 | 0 | 0 | 0
Valve Data Sheet | Engineering | 1 | 0 | 2500 | 0 | 0 | 0
Instrument Data Sheet | Engineering | 1 | 0 | 2500 | 0 | 0 | 0
Logic Map | Engineering | 5 | 0 | 6666 | 0 | 0 | 0
Instruments List | Engineering | 2 | 0 | 6666 | 0 | 0 | 0
Pneumatic Calculation | Engineering | 3 | 0 | 6666 | 0 | 0 | 0
Piping Class | Engineering | 2 | 0 | 0 | 0 | 0 | 1120
Painting Procedure | Engineering | 2 | 0 | 0 | 0 | 0 | 1120
Valve List | Engineering | 2 | 0 | 0 | 0 | 0 | 1120
P&ID | Engineering | 5 | 0 | 0 | 0 | 0 | 2800
BOM BOP | Engineering | 2 | 0 | 6000 | 0 | 0 | 0
General Arrangement | Engineering | 1 | 0 | 6000 | 0 | 0 | 0
Isometric DWG | Engineering | 5 | 0 | 6000 | 0 | 0 | 0
Structures DWG | Engineering | 3 | 0 | 6000 | 0 | 0 | 0
3D Model | Engineering | 20 | 0 | 6000 | 0 | 0 | 0
Control Panel Logic | Engineering | 25 | 0 | 8000 | 0 | 0 | 0
Control Systems | Engineering | 10 | 0 | 8000 | 0 | 0 | 0
Electrical Hook-Up | Engineering | 25 | 0 | 8333 | 0 | 0 | 0
Wiring Diagram | Engineering | 10 | 0 | 8333 | 0 | 0 | 0
Pneumatic Hook-up | Engineering | 10 | 0 | 8333 | 0 | 0 | 0
Filter | Procurment | 140 | 0 | 0 | 6000 | 0 | 0
Sterilizer&mineralizer | Procurment | 150 | 0 | 0 | 7000 | 0 | 0
Pump | Procurment | 150 | 0 | 0 | 8000 | 0 | 0
Fitting | Procurment | 30 | 10000 | 0 | 0 | 0 | 0
Flanges | Procurment | 40 | 4000 | 0 | 0 | 0 | 0
Gaskets | Procurment | 25 | 1500 | 0 | 0 | 0 | 0
Stud&Nuts | Procurment | 15 | 1000 | 0 | 0 | 0 | 0
Manual Valves | Procurment | 90 | 0 | 0 | 3000 | 0 | 0
Actuated Valves | Procurment | 120 | 0 | 0 | 10000 | 0 | 0
ESD valves | Procurment | 130 | 0 | 0 | 8000 | 0 | 0
Flow Computer | Procurment | 170 | 0 | 0 | 12000 | 0 | 0
P/T Gauges | Procurment | 25 | 0 | 0 | 900 | 0 | 0
P/T Transimitters | Procurment | 60 | 0 | 0 | 4000 | 0 | 0
Level Transmitter | Procurment | 90 | 0 | 0 | 8000 | 0 | 0
Flow Orifices | Procurment | 40 | 0 | 0 | 1300 | 0 | 0
JBs | Procurment | 25 | 0 | 0 | 500 | 0 | 0
Steelworks&support Material | Procurment | 20 | 5000 | 0 | 0 | 0 | 0
Structures Prefabbrication | Construction | 5 | 0 | 0 | 0 | 2000 | 0
Painting Structures | Construction | 10 | 0 | 0 | 7000 | 0 | 0
Piping Prefabbrication | Construction | 35 | 0 | 0 |  | 14000 | 0
Pickling | Construction | 5 | 0 | 0 | 3000 | 0 | 0
Painting Piping | Construction | 15 | 0 | 0 | 21000 | 0 | 0
Equipment | Construction | 1 | 0 | 0 | 0 | 400 | 0
Piping | Construction | 5 | 0 | 0 | 0 | 2000 | 0
Valves | Construction | 5 | 0 | 0 | 0 | 2000 | 0
instruments | Construction | 5 | 0 | 0 | 5400 | 0 | 0
JBs | Construction | 2 | 0 | 0 | 5400 | 0 | 0
cables & cabletray | Construction | 10 | 0 | 0 | 5400 | 0 | 0
Actuated Valve Setup | Construction | 2 | 0 | 0 | 5400 | 0 | 0
tubing | Construction | 10 | 0 | 0 | 5400 | 0 | 0
Pump | Testing | 0.5 | 0 | 0 | 0 | 200 | 0
Sterilizer&Mineralizer | Testing | 0.5 | 0 | 0 | 0 | 200 | 0
Filter | Testing | 0.5 | 0 | 0 | 0 | 200 | 0
Contol Panel | Testing | 0.5 | 0 | 0 | 0 | 200 | 0
Assembled Skid | Testing | 1 | 0 | 0 | 0 | 400 | 0
NDT on Weldings (structure) | Testing | 1 | 0 | 0 | 100 | 400 | 0
Dimensional Check (Structure) | Testing | 0.5 | 0 | 0 | 100 | 200 | 0
Painting Check (Structure) | Testing | 0.5 | 0 | 0 | 100 | 200 | 0
NDT on Weldings (piping) | Testing | 1 | 0 | 0 | 200 | 400 | 0
Dimensional Check (piping) | Testing | 0.5 | 0 | 0 | 200 | 200 | 0
HydroStatic Pressure TEst | Testing | 3 | 0 | 0 | 200 | 1200 | 0
Painting Check (piping) | Testing | 1 | 0 | 0 | 0 | 400 | 0
Observer (Third Party) | Testing | 3 | 0 | 0 | 8000 | 0 | 0
Dimensional Check | Testing | 0.5 | 0 | 0 | 0 | 200 | 0
IECEx Detailed Test | Testing | 3 | 0 | 0 | 0 | 1200 | 0
Automation Test | Testing | 1 | 0 | 0 | 0 | 400 | 0
Final Tests | Testing | 1 | 0 | 0 | 0 | 400 | 0
Documentation Pack | Testing | 2 | 0 | 0 | 0 | 0 | 1120