## Sheet1
Name | Duration | Section | Parents | Materials | External Engineering | Supplier | Internal Manpower | Internal Engineering
PFD - Heat&Mass Balance | 13 | Engineering |  | 0 | 2500 | 0 | 0 | 0
Filter Procurement | 1 | Procurement | Filter Data Sheet | 0 | 0 | 0 | 0 | 0
Filter Data Sheet | 1 | Engineering | PFD - Heat&Mass Balance | 0 | 2500 | 0 | 0 | 0
Pump Data Sheet | 1 | Engineering | PFD - Heat&Mass Balance | 0 | 2500 | 0 | 0 | 0
Sterilizer&mineralizer DS | 1 | Engineering | PFD - Heat&Mass Balance | 0 | 2500 | 0 | 0 | 0
Valve Data Sheet | 1 | Engineering | PFD - Heat&Mass Balance | 0 | 2500 | 0 | 0 | 0
Instrument Data Sheet | 1 | Engineering | PFD - Heat&Mass Balance | 0 | 2500 | 0 | 0 | 0
Logic Map | 5 | Engineering | PFD - Heat&Mass Balance, P&ID | 0 | 6666 | 0 | 0 | 0
Instruments List | 2 | Engineering | P&ID | 0 | 6666 | 0 | 0 | 0
Pneumatic Calculation | 3 | Engineering | Instruments List | 0 | 6666 | 0 | 0 | 0
Piping Class | 2 | Engineering | Pneumatic Calculation | 0 | 0 | 0 | 0 | 1120
Painting Procedure | 2 | Engineering | PFD - Heat&Mass Balance | 0 | 0 | 0 | 0 | 1120
Valve List | 2 | Engineering | P&ID | 0 | 0 | 0 | 0 | 1120
P&ID | 5 | Engineering | PFD - Heat&Mass Balance, Piping Class | 0 | 0 | 0 | 0 | 2800
BOM BOP | 2 | Engineering | 3D Model | 0 | 6000 | 0 | 0 | 0
General Arrangement | 1 | Engineering | BOM BOP | 0 | 6000 | 0 | 0 | 0
Isometric DWG | 5 | Engineering |  | 0 | 6000 | 0 | 0 | 0
Structures DWG | 3 | Engineering |  | 0 | 6000 | 0 | 0 | 0
3D Model | 20 | Engineering | P&ID | 0 | 6000 | 0 | 0 | 0
Control Panel Logic | 25 | Engineering | Logic Map | 0 | 8000 | 0 | 0 | 0
Control Systems | 10 | Engineering | Logic Map | 0 | 8000 | 0 | 0 | 0
Electrical Hook-Up | 25 | Engineering | Control Systems | 0 | 8333 | 0 | 0 | 0
Wiring Diagram | 10 | Engineering | Control Panel Logic | 0 | 8333 | 0 | 0 | 0
Pneumatic Hook-Up | 10 | Engineering | Wiring Diagram | 0 | 8333 | 0 | 0 | 0
Filter | 140 | Procurement | Pneumatic Hook-Up | 0 | 0 | 6000 | 0 | 0
Sterilizer&mineralizer | 150 | Procurement | Filter | 0 | 0 | 7000 | 0 | 0
Pump | 150 | Procurement | Sterilizer&mineralizer | 0 | 0 | 8000 | 0 | 0
Fitting | 30 | Procurement | Pump | 10000 | 0 | 0 | 0 | 0
Flanges | 40 | Procurement | Fitting | 4000 | 0 | 0 | 0 | 0
Gaskets | 25 | Procurement | Flanges | 1500 | 0 | 0 | 0 | 0
Stud&Nuts | 15 | Procurement | Gaskets | 1000 | 0 | 0 | 0 | 0
Manual Valves | 90 | Procurement | Stud&Nuts | 0 | 0 | 3000 | 0 | 0
Actuated Valves | 120 | Procurement | Manual Valves | 0 | 0 | 10000 | 0 | 0
ESD valves | 130 | Procurement | Actuated Valves | 0 | 0 | 8000 | 0 | 0
Flow Computer | 170 | Procurement | Control Panel Logic, P&ID | 0 | 0 | 12000 | 0 | 0
P/T Gauges | 25 | Procurement | Flow Computer | 0 | 0 | 900 | 0 | 0
P/T Transmitters | 60 | Procurement | P/T Gauges | 0 | 0 | 4000 | 0 | 0
Level Transmitter | 90 | Procurement | P/T Transmitters | 0 | 0 | 8000 | 0 | 0
Flow Orifices | 40 | Procurement | Level Transmitter | 0 | 0 | 1300 | 0 | 0
JBs Procurement | 25 | Procurement | Flow Orifices | 0 | 0 | 500 | 0 | 0
Steelworks&support Material | 20 | Procurement | JBs Procurement | 5000 | 0 | 0 | 0 | 0
Structures Prefabbrication | 5 | Construction | Steelworks&support Material | 0 | 0 | 0 | 2000 | 0
Painting Structures | 10 | Construction | Structures Prefabbrication | 0 | 0 | 7000 | 0 | 0
Piping Prefabbrication | 35 | Construction | Painting Structures | 0 | 0 | 0 | 14000 | 0
Pickling | 5 | Construction | Piping Prefabbrication | 0 | 0 | 3000 | 0 | 0
Painting Piping | 15 | Construction | Painting Procedure | 0 | 0 | 21000 | 0 | 0
Equipment | 1 | Construction | Painting Piping | 0 | 0 | 0 | 400 | 0
Piping | 5 | Construction | Equipment | 0 | 0 | 0 | 2000 | 0
Valves | 5 | Construction | Piping | 0 | 0 | 0 | 2000 | 0
Instruments Installation | 5 | Construction | Valves | 0 | 0 | 5400 | 0 | 0
JBs Installation | 2 | Construction | Instruments Installation | 0 | 0 | 5400 | 0 | 0
Cable & Cabletray Installation | 10 | Construction | JBs Installation | 0 | 0 | 5400 | 0 | 0
Actuated Valve Setup | 2 | Construction | Cable & Cabletray Installation | 0 | 0 | 5400 | 0 | 0
Tubing | 10 | Construction | Actuated Valve Setup | 0 | 0 | 0 | 0 | 0
Pump Test | 0 | Testing | Tubing | 0 | 0 | 0 | 200 | 0
Sterilizer&mineralizer Test | 0 | Testing | Pump Test | 0 | 0 | 0 | 200 | 0
Filter Test | 0 | Testing | Sterilizer&mineralizer Test | 0 | 0 | 0 | 200 | 0
Control Panel Test | 0 | Testing | Filter Test | 0 | 0 | 0 | 200 | 0
Assembled Skid | 1 | Testing | Control Panel Test | 0 | 0 | 0 | 400 | 0
NDT on Weldings (Structure) | 1 | Testing | Assembled Skid | 0 | 0 | 100 | 400 | 0
Dimensional Check (Structure) | 0 | Testing | NDT on Weldings (Structure) | 0 | 0 | 100 | 200 | 0
Painting Check (Structure) | 0 | Testing | Dimensional Check (Structure) | 0 | 0 | 100 | 200 | 0
NDT on Weldings (Piping) | 1 | Testing | Painting Check (Structure) | 0 | 0 | 200 | 400 | 0
Dimensional Check (Piping) | 0 | Testing | NDT on Weldings (Piping) | 0 | 0 | 200 | 200 | 0
Hydrostatic Pressure Test | 3 | Testing |  | 0 | 0 | 200 | 1200 | 0
Painting Check (Piping) | 1 | Testing | Hydrostatic Pressure Test | 0 | 0 | 0 | 400 | 0
Observer (Third Party) | 3 | Testing | Painting Check (Piping) | 0 | 0 | 8000 | 0 | 0
Dimensional Check (Observer) | 0 | Testing | Observer (Third Party) | 0 | 0 | 0 | 200 | 0
IECEx Detailed Test | 3 | Testing | Automation Test, Control Systems | 0 | 0 | 0 | 1200 | 0
Automation Test | 1 | Testing |  | 0 | 0 | 0 | 400 | 0
Final Tests | 1 | Testing | Automation Test | 0 | 0 | 0 | 400 | 0
Documentation Pack | 2 | Testing | Final Tests | 0 | 0 | 0 | 0 | 1120