## Foglio1 (2)
290577
[13 empty] | External Costs |  |  | Internal Costs
[13 empty] | 255097 |  |  | 35480
TOT |  |  |  | tot | WBS | tot | d | Task | Time [days] | Task Cost | Parents | Comments | Materials | External Enginering | Supplier | Manpower 3 people [50€/h] | Internal Engineering 2 people [70€/h]
[13 empty] | 21500 | 105997 | 127600 | 28200 | 7280
290577 | Engineering | 112157 | Process | 41158 | Chemical Process | 15000 | 18 | PFD - Heat&Mass Balance | 13 | 2500 |  |  | 0 | 2500 | 0 | 0 | 0
| Engineering | [6 empty] | Filter Data Sheet | 1 | 2500 | PFD - Heat&Mass Balance |  | 0 | 2500 | 0 | 0 | 0
| Engineering | [6 empty] | Pump Data Sheet | 1 | 2500 | PFD - Heat&Mass Balance |  | 0 | 2500 | 0 | 0 | 0
| Engineering | [6 empty] | Sterilizer&Mineralizer DS | 1 | 2500 | PFD - Heat&Mass Balance |  | 0 | 2500 | 0 | 0 | 0
| Engineering | [6 empty] | Valve Data Sheet | 1 | 2500 | PFD - Heat&Mass Balance, Valve List |  | 0 | 2500 | 0 | 0 | 0
| Engineering | [6 empty] | Instruments Data Sheet | 1 | 2500 | PFD - Heat&Mass Balance, Instruments List |  | 0 | 2500 | 0 | 0 | 0
| Engineering |  |  |  | Automation Logic | 19998 | 10 | Logic Map | 5 | 6666 | PFD - Heat&Mass Balance, P&ID |  | 0 | 6666 | 0 | 0 | 0
| Engineering | [6 empty] | Instruments List | 2 | 6666 | P&ID |  | 0 | 6666 | 0 | 0 | 0
| Engineering | [6 empty] | Pneumatic Calculation | 3 | 6666 | Instruments List |  | 0 | 6666 | 0 | 0 | 0
| Engineering |  |  |  | Mechanical Process | 6160 | 11 | Piping Class | 2 | 1120 | PFD - Heat&Mass Balance |  | 0 | 0 | 0 | 0 | 1120
| Engineering | [6 empty] | Painting Procedure | 2 | 1120 | PFD - Heat&Mass Balance |  | 0 | 0 | 0 | 0 | 1120
| Engineering | [6 empty] | Valve List | 2 | 1120 | PFD - Heat&Mass Balance, P&ID |  | 0 | 0 | 0 | 0 | 1120
| Engineering | [6 empty] | P&ID | 5 | 2800 | PFD - Heat&Mass Balance |  | 0 | 0 | 0 | 0 | 2800
| Engineering |  | Mechanical | 30000 | BOM | 6000 | 2 | BOM BOP | 2 | 6000 | 3D Model, P&ID, Valve List, Instruments List, Piping Class |  | 0 | 6000 | 0 | 0 | 0
| Engineering |  |  |  | Technical Drawing | 18000 | 9 | General Arrangement | 1 | 6000 | 3D Model |  | 0 | 6000 | 0 | 0 | 0
| Engineering | [6 empty] | Isometric DWG | 5 | 6000 | General Arrangement, Piping Class |  | 0 | 6000 | 0 | 0 | 0
| Engineering | [6 empty] | Structures DWG | 3 | 6000 | General Arrangement |  | 0 | 6000 | 0 | 0 | 0
| Engineering |  |  |  | 3D Model | 6000 | 20 | 3D Model | 20 | 6000 | P&ID | a 10g prima -> GA preliminare, a 12 prima -> BOM preliminare. una volta concluso £D model, avremo GA Finale e BOM definitiva Approvati. Ricordiamo che c'è da considerare ricezione MEchanical dwg dai vari procurement (sopratutto equipment, le valvole hanno scartamenti standard, ma per ingombri, soprattutto le attuate, si dovrebbero avere i dsegni tecnici) | 0 | 6000 | 0 | 0 | 0
| Engineering |  | Automation | 40999 | Flowcomputer Logic | 16000 | 35 | Control Panel Logic | 25 | 8000 | Logic Map |  | 0 | 8000 | 0 | 0 | 0
| Engineering | [6 empty] | Control Systems | 10 | 8000 | Logic Map, Instruments Data Sheet, Wiring Diagram, Control Panel Logic | -> Control Panel FAT, Automation final test, IECEx Detailed Test, Assembled Skid FAT | 0 | 8000 | 0 | 0 | 0
| Engineering |  |  |  | Electrical&Pneumatic | 24999 | 45 | Electrical Hook-Up | 25 | 8333 | Control Panel Logic | -> E&I installation, Automation Test, IECEx Test | 0 | 8333 | 0 | 0 | 0
| Engineering | [6 empty] | Wiring Diagram | 10 | 8333 | Control Panel Logic | - cable & cabletray installation, JBs installation, FAT control Panel | 0 | 8333 | 0 | 0 | 0
| Engineering | [6 empty] | Pneumatic Hook-up | 10 | 8333 | Pneumatic Calculation | -> E&I installation, Mechanical Erection(Actuated, ESD Valves), tubing Construction, FAT Assembled Skid | 0 | 8333 | 0 | 0 | 0
| Procurement | 90200 | Critical Components | 21000 | Filter | 6000 | 140 | Filter Procurement | 140 | 6000 | Filter Data Sheet |  | 0 | 0 | 6000 | 0 | 0
| Procurement |  |  |  | Sterilizer&Mineralizer | 7000 | 150 | Sterilizer&Mineralizer Procurement | 150 | 7000 | Sterilizer&Mineralizer DS |  | 0 | 0 | 7000 | 0 | 0
| Procurement |  |  |  | Pump | 8000 | 150 | Pump Procurement | 150 | 8000 | Pump Data Sheet |  | 0 | 0 | 8000 | 0 | 0
| Procurement |  | Accessories | 69200 | Bulk Piping | 16500 | 110 | Fitting Procurement | 30 | 10000 | BOM BOP |  | 10000 | 0 | 0 | 0 | 0
| Procurement | [6 empty] | Flanges Procurement | 40 | 4000 | BOM BOP |  | 4000 | 0 | 0 | 0 | 0
| Procurement | [6 empty] | Gaskets Procurement | 25 | 1500 | BOM BOP |  | 1500 | 0 | 0 | 0 | 0
| Procurement | [6 empty] | Stud&Nuts Procurement | 15 | 1000 | BOM BOP |  | 1000 | 0 | 0 | 0 | 0
| Procurement |  |  |  | Valves | 21000 | 340 | Manual Valves Procurement | 90 | 3000 | Valve Data Sheet | -> mechanical Erection | 0 | 0 | 3000 | 0 | 0
| Procurement | [6 empty] | Actuated Valves Procurement | 120 | 10000 | Valve Data Sheet, Logic Map | -> mechanical Erection | 0 | 0 | 10000 | 0 | 0
| Procurement | [6 empty] | ESD valves Procurement | 130 | 8000 | Valve Data Sheet, Logic Map | -> mechanical Erection | 0 | 0 | 8000 | 0 | 0
| Procurement |  |  |  | flow computer | 12000 | 170 | Flow Computer Procurement | 170 | 12000 | Instruments Data Sheet, Control Panel Logic, Control Systems | -> E&I Erection | 0 | 0 | 12000 | 0 | 0
| Procurement |  |  |  | Instruments | 14700 | 240 | P/T Gauges Procurement | 25 | 900 | Instruments Data Sheet | -> E&I Erection | 0 | 0 | 900 | 0 | 0
| Procurement | [6 empty] | P/T Transimitters Procurement | 60 | 4000 | Instruments Data Sheet | -> E&I Erection | 0 | 0 | 4000 | 0 | 0
| Procurement | [6 empty] | Level Transmitter Procurement | 90 | 8000 | Instruments Data Sheet | -> E&I Erection | 0 | 0 | 8000 | 0 | 0
| Procurement | [6 empty] | Flow Orifices Procurement | 40 | 1300 | Instruments Data Sheet | -> E&I Erection | 0 | 0 | 1300 | 0 | 0
| Procurement | [6 empty] | JBs Procurement | 25 | 500 | Instruments Data Sheet | -> E&I Erection | 0 | 0 | 500 | 0 | 0
| Procurement |  |  |  | Steelworks | 5000 | 20 | Steelworks&support Material Procurement | 20 | 5000 | Structures DWG, BOM BOP | -> Structures Prefabrication | 5000 | 0 | 0 | 0 | 0
| Construction | 78400 | Mechanical Prefabrication | 47000 | Structures Prefabrication | 2000 | 5 | Structures Prefabrication | 5 | 2000 | Structures DWG, Steelworks&support Material Procurement | -> NDT on weldings structure | 0 | 0 | 0 | 2000 | 0
| Construction |  |  |  | Painting Structures | 7000 | 10 | Painting Structures | 10 | 7000 | Painting Procedure, Dimensional Check (Structures), Structures Prefabrication | -> painting check structures | 0 | 0 | 7000 | 0 | 0
| Construction |  |  |  | Piping Prefabrication | 14000 | 35 | Piping Prefabrication | 35 | 14000 | Isometric DWG, Fitting Procurement, Flanges Procurement, Gaskets Procurement, Stud&Nuts Procurement, Piping Class | -> NDT on wedings Piping | 0 | 0 |  | 14000 | 0
| Construction |  |  |  | Pickling | 3000 | 5 | Pickling | 5 | 3000 | Hydrostatic Pressure Test | -> painting piping | 0 | 0 | 3000 | 0 | 0
| Construction |  |  |  | Painting Piping | 21000 | 15 | Painting Piping | 15 | 21000 | Painting Procedure, Pickling | -> painting check piping | 0 | 0 | 21000 | 0 | 0
| Construction |  | Mechanical Erection | 4400 | Equipment | 400 | 1 | Equipment Erection | 1 | 400 | Pneumatic Hook-up, Painting Check (Structure), Pump FAT, Sterilizer&Mineralizer FAT, Filter FAT | -> E&I installation, FAT assembled Skdi | 0 | 0 | 0 | 400 | 0
| Construction |  |  |  | Piping | 2000 | 5 | Piping Erection | 5 | 2000 | Pneumatic Hook-up, Painting Check (Structure), Painting Check (Piping) |  | 0 | 0 | 0 | 2000 | 0
| Construction |  |  |  | Valves | 2000 | 5 | Valves Erection | 5 | 2000 | Pneumatic Hook-up, Painting Check (Structure), ESD valves Procurement, Manual Valves Procurement, Actuated Valves Procurement |  | 0 | 0 | 0 | 2000 | 0
| Construction |  | Electrical & Instrument Installation | 27000 | Instruments | 27000 | 29 | Instruments Installation | 5 | 5400 | Electrical Hook-Up, Pneumatic Hook-up, P/T Gauges Procurement, P/T Transimitters Procurement, Level Transmitter Procurement, Flow Orifices Procurement | ipotizzo 3/4 persone, -> IECEx Test, Automation TEst | 0 | 0 | 5400 | 0 | 0
| Construction |  |  |  | JBs |  |  | JBs Installation | 2 | 5400 | Electrical Hook-Up, Flow Computer Procurement, JBs Procurement |  | 0 | 0 | 5400 | 0 | 0
| Construction |  |  |  | cables & cabletray |  |  | cables & cabletray Installation | 10 | 5400 | Electrical Hook-Up, Valve List, Pneumatic Hook-up, Instruments Installation, JBs Installation |  | 0 | 0 | 5400 | 0 | 0
| Construction |  |  |  | Actuated Valve Setup |  |  | Actuated Valve Setup Installation | 2 | 5400 | Electrical Hook-Up, Valve List, Pneumatic Hook-up, Valves Erection |  | 0 | 0 | 5400 | 0 | 0
| Construction |  |  |  | tubing Construction |  |  | tubing Installation | 10 | 5400 | Pneumatic Hook-up, Flow Computer FAT |  | 0 | 0 | 5400 | 0 | 0
| Testing | 9820 | FATs Procedure | 2000 | Equipment FAT | 400 | 3 | Pump FAT | 1 | 400 | Pump Procurement | -> mechanical erection equipment | 0 | 0 | 0 | 400 | 0
| Testing |  |  |  |  | 400 |  | Sterilizer&Mineralizer FAT | 1 | 400 | Sterilizer&Mineralizer Procurement |  | 0 | 0 | 0 | 400 | 0
| Testing |  |  |  |  | 400 |  | Filter FAT | 1 | 400 | Filter Procurement |  | 0 | 0 | 0 | 400 | 0
| Testing |  |  |  | Outside Skid FAT | 400 | 1 | Flow Computer FAT | 1 | 400 | Flow Computer Procurement | -> E&I installation | 0 | 0 | 0 | 400 | 0
| Testing |  |  |  | Assembled Skid FAT | 400 | 1 | Assembled Skid FAT | 1 | 400 | Equipment Erection, Piping Erection, Valves Erection, Instruments Installation, JBs Installation, cables & cabletray Installation, Actuated Valve Setup Installation, tubing Installation, Dimensional Check (Assembled) | -> ,Automation TEst, Final Test | 0 | 0 | 0 | 400 | 0
| Testing |  | Skid | 7820 | Structure | 1500 | 3 | NDT on Weldings (Structure) | 1 | 500 | Structures Prefabrication | -> dimensional check structures | 0 | 0 | 100 | 400 | 0
| Testing | [6 empty] | Dimensional Check (Structures) | 1 | 500 | NDT on Weldings (Structure) | -Painting structure | 0 | 0 | 100 | 400 | 0
| Testing | [6 empty] | Painting Check (Structure) | 1 | 500 | Painting Structures | -> mechanical erection | 0 | 0 | 100 | 400 | 0
| Testing |  |  |  | Piping | 3000 | 6 | NDT on Weldings (Piping) | 1 | 600 | Piping Prefabrication | -> dimensional Check | 0 | 0 | 200 | 400 | 0
| Testing | [6 empty] | Dimensional Check | 1 | 600 | NDT on Weldings (Piping), NDT on Weldings (Structure) | -> hydrostatic Pressure Test | 0 | 0 | 200 | 400 | 0
| Testing | [6 empty] | Hydrostatic Pressure Test | 3 | 1400 | Dimensional Check | -> pickling | 0 | 0 | 200 | 1200 | 0
| Testing | [6 empty] | Painting Check (Piping) | 1 | 400 | Painting Piping | -> Mechanical Erection | 0 | 0 | 0 | 400 | 0
| Testing |  |  |  | Assembled Skid | 3320 | 7.5 | Dimensional Check (Assembled) | 0.5 | 200 | Equipment Erection, Piping Erection, Valves Erection, Instruments Installation, JBs Installation, cables & cabletray Installation, Actuated Valve Setup Installation, tubing Installation | questi sono in ordine e non uno dopo l'altro, quindi regolate di conseguenza con le altre relazioni precedenti | 0 | 0 | 0 | 200 | 0
| Testing | [6 empty] | IECEx Detailed Test | 3 | 1200 | Control Systems, Electrical Hook-Up, Instruments Installation, tubing Installation, Dimensional Check (Assembled), JBs Installation, cables & cabletray Installation |  | 0 | 0 | 0 | 1200 | 0
| Testing | [6 empty] | Automation Test | 1 | 400 | IECEx Detailed Test |  | 0 | 0 | 0 | 400 | 0
| Testing | [6 empty] | Final Tests | 1 | 400 | Automation Test, Assembled Skid FAT |  | 0 | 0 | 0 | 400 | 0
| Testing | [6 empty] | Documentation Pack | 2 | 1120 | Final Tests |  | 0 | 0 | 0 | 0 | 1120

## Foglio1
Task | Parents
PFD - Heat&Mass Balance
Filter Data Sheet | PFD - Heat&Mass Balance
Pump Data Sheet | PFD - Heat&Mass Balance
Sterilizer&mineralizer DS | PFD - Heat&Mass Balance
Valve Data Sheet | PFD - Heat&Mass Balance, Valve List
Instruments Data Sheet | PFD - Heat&Mass Balance, Instruments List
Logic Map | PFD - Heat&Mass Balance, P&ID
Instruments List | P&ID
Pneumatic Calculation | Instruments List
Piping Class | PFD - Heat&Mass Balance
Painting Procedure | PFD - Heat&Mass Balance
Valve List | PFD - Heat&Mass Balance, P&ID
P&ID | PFD - Heat&Mass Balance
BOM BOP | 3D Model, P&ID, Valve List, Instruments List, Piping Class
General Arrangement | 3D Model
Isometric DWG | General Arrangement, Piping Class
Structures DWG | General Arrangement
3D Model | P&ID
Control Panel Logic | Logic Map
Control Systems | Logic Map, Instruments Data Sheet, Wiring Diagram, Control Panel Logic
Electrical Hook-Up | Control Panel Logic
Wiring Diagram | Control Panel Logic
Pneumatic Hook-up | Pneumatic Calculation
Filter Procurement | Filter Data Sheet
Sterilizer&mineralizer Procurement | Sterilizer&mineralizer DS
Pump Procurement | Pump Data Sheet
Fitting Procurement | BOM BOP
Flanges Procurement | BOM BOP
Gaskets Procurement | BOM BOP
Stud&Nuts Procurement | BOM BOP
Manual Valves Procurement | Valve Data Sheet
Actuated Valves Procurement | Valve Data Sheet, Logic Map
ESD valves Procurement | Valve Data Sheet, Logic Map
Flow Computer Procurement | Instrument Data Sheet, Control Panel Logic, Control Systems
P/T Gauges Procurement | Instruments Data Sheet
P/T Transimitters Procurement | Instruments Data Sheet
Level Transmitter Procurement | Instruments Data Sheet
Flow Orifices Procurement | Instruments Data Sheet
JBs Procurement | Instruments Data Sheet
Steelworks&support Material Procurement | Structures DWG, BOM BOP
Structures Prefabbrication | Structures DWG, Steelworks&support Material Procurement
Painting Structures | Painting Procedure, Dimensional Check (Structures), Structures Prefabbrication
Piping Prefabbrication | Isometric DWG, Fitting Procurement, Flanges Procurement, Gaskets Procurement, Stud&Nuts Procurement, Piping Class
Pickling | Hydrostatic Pressure Test
Painting Piping | Painting Procedure, Pickling
Equipment Erection | Pneumatic Hook-up, Painting Check (Sructure), Pump FAT, Sterilizer&Mineralizer FAT, Filter FAT
Piping Erection | Pneumatic Hook-up, Painting Check (Structure), Painting Check (Piping)
Valves Erection | Pneumatic Hook-up, Painting Check (Sructure), ESD valves Procurement, Manual Valves Procurement, Actuated Valve Procurement
instruments Installation | Electrical Hook-Up, Pneumatic Hook-up, P/T Gauges Procurement, P/T Transimitters Procurement, Level Transmitter Procurement, Flow Orifices Procurement
JBs Installation | Electrical Hook-Up, Flow Computer FAT, JBs Procurement
cables & cabletray Installation | Electrical Hook-Up, Valve List, Pneumatic Hook-up, Instruments Installation, JBs Installation
Actuated Valve Setup Installation | Electrical Hook-Up, Valve List, Pneumatic Hook-up, Valves Erection
tubing Installation | Pneumatic Hook-up, Flow Computer FAT
Pump FAT | Pump Procurement
Sterilizer&Mineralizer FAT | Sterilizer&mineralizer Procurement
Filter FAT | Filter Procurement
Flow Computer FAT | Flow Computer Procurement
Assembled Skid FAT | Equipment Erection, Piping Erection, Valves Erection, instruments Installation, JBs Installation, cables & cabletray Installation, Actuated Valve Setup Installation, tubing Installation, Dimensional Check (Assembled)
NDT on Weldings (Structure) | Structures Prefabbrication Construction
Dimensional Check (Structures) | NDT on Weldings (Structure)
Painting Check (Structure) | Painting Structures Construction
NDT on Weldings (Piping) | Piping Prefabbrication Construction
Dimensional Check | NDT on Weldings (Piping), NDT on Weldings (Structure)
Hydrostatic Pressure Test | Dimensional Check
Painting Check (Piping) | Painting Piping
Observer (Third Party) | *NO GANTT*
Dimensional Check (Assembled) | Equipment Erection, Piping Erection, Valves Erection, instruments Installation, JBs Installation, cables & cabletray Installation, Actuated Valve Setup Installation, tubing Installation
IECEx Detailed Test | Control Systems, Electrical Hook-Up, instruments Installation, tubing Installation, Dimensional Check (Assembled), JBs Installation, cables & cabletray Installation
Automation Test | IECEx Detailed Test
Final Tests | Automation Test, Assembled Skid FAT
Documentation Pack | Final Tests

## Foglio2
task name |  | duration | materials cost | ext engineering | supplier | manpower | internal engineerign
PFD - Heat&Mass Balance | Engineering | 13 | 0 | 2500 | 0 | 0 | 0
Filter Data Sheet | Engineering | 1 | 0 | 2500 | 0 | 0 | 0
Pump Data Sheet | Engineering | 1 | 0 | 2500 | 0 | 0 | 0
Sterilizer&mineralizer DS | Engineering | 1 | 0 | 2500 | 0 | 0 | 0
Valve Data Sheet | Engineering | 1 | 0 | 2500 | 0 | 0 | 0
Instrument Data Sheet | Engineering | 1 | 0 | 2500 | 0 | 0 | 0
Logic Map | Engineering | 5 | 0 | 6666 | 0 | 0 | 0
Instruments List | Engineering | 2 | 0 | 6666 | 0 | 0 | 0
Pneumatic Calculation | Engineering | 3 | 0 | 6666 | 0 | 0 | 0
Piping Class | Engineering | 2 | 0 | 0 | 0 | 0 | 1120
Painting Procedure | Engineering | 2 | 0 | 0 | 0 | 0 | 1120
Valve List | Engineering | 2 | 0 | 0 | 0 | 0 | 1120
P&ID | Engineering | 5 | 0 | 0 | 0 | 0 | 2800
BOM BOP | Engineering | 2 | 0 | 6000 | 0 | 0 | 0
General Arrangement | Engineering | 1 | 0 | 6000 | 0 | 0 | 0
Isometric DWG | Engineering | 5 | 0 | 6000 | 0 | 0 | 0
Structures DWG | Engineering | 3 | 0 | 6000 | 0 | 0 | 0
3D Model | Engineering | 20 | 0 | 6000 | 0 | 0 | 0
Control Panel Logic | Engineering | 25 | 0 | 8000 | 0 | 0 | 0
Control Systems | Engineering | 10 | 0 | 8000 | 0 | 0 | 0
Electrical Hook-Up | Engineering | 25 | 0 | 8333 | 0 | 0 | 0
Wiring Diagram | Engineering | 10 | 0 | 8333 | 0 | 0 | 0
Pneumatic Hook-up | Engineering | 10 | 0 | 8333 | 0 | 0 | 0
Filter | Procurment | 140 | 0 | 0 | 6000 | 0 | 0
Sterilizer&mineralizer | Procurment | 150 | 0 | 0 | 7000 | 0 | 0
Pump | Procurment | 150 | 0 | 0 | 8000 | 0 | 0
Fitting | Procurment | 30 | 10000 | 0 | 0 | 0 | 0
Flanges | Procurment | 40 | 4000 | 0 | 0 | 0 | 0
Gaskets | Procurment | 25 | 1500 | 0 | 0 | 0 | 0
Stud&Nuts | Procurment | 15 | 1000 | 0 | 0 | 0 | 0
Manual Valves | Procurment | 90 | 0 | 0 | 3000 | 0 | 0
Actuated Valves | Procurment | 120 | 0 | 0 | 10000 | 0 | 0
ESD valves | Procurment | 130 | 0 | 0 | 8000 | 0 | 0
Flow Computer | Procurment | 170 | 0 | 0 | 12000 | 0 | 0
P/T Gauges | Procurment | 25 | 0 | 0 | 900 | 0 | 0
P/T Transimitters | Procurment | 60 | 0 | 0 | 4000 | 0 | 0
Level Transmitter | Procurment | 90 | 0 | 0 | 8000 | 0 | 0
Flow Orifices | Procurment | 40 | 0 | 0 | 1300 | 0 | 0
JBs | Procurment | 25 | 0 | 0 | 500 | 0 | 0
Steelworks&support Material | Procurment | 20 | 5000 | 0 | 0 | 0 | 0
Structures Prefabbrication | Construction | 5 | 0 | 0 | 0 | 2000 | 0
Painting Structures | Construction | 10 | 0 | 0 | 7000 | 0 | 0
Piping Prefabbrication | Construction | 35 | 0 | 0 |  | 14000 | 0
Pickling | Construction | 5 | 0 | 0 | 3000 | 0 | 0
Painting Piping | Construction | 15 | 0 | 0 | 21000 | 0 | 0
Equipment | Construction | 1 | 0 | 0 | 0 | 400 | 0
Piping | Construction | 5 | 0 | 0 | 0 | 2000 | 0
Valves | Construction | 5 | 0 | 0 | 0 | 2000 | 0
instruments | Construction | 5 | 0 | 0 | 5400 | 0 | 0
JBs | Construction | 2 | 0 | 0 | 5400 | 0 | 0
cables & cabletray | Construction | 10 | 0 | 0 | 5400 | 0 | 0
Actuated Valve Setup | Construction | 2 | 0 | 0 | 5400 | 0 | 0
tubing | Construction | 10 | 0 | 0 | 5400 | 0 | 0
Pump | Testing | 0.5 | 0 | 0 | 0 | 200 | 0
Sterilizer&Mineralizer | Testing | 0.5 | 0 | 0 | 0 | 200 | 0
Filter | Testing | 0.5 | 0 | 0 | 0 | 200 | 0
Contol Panel | Testing | 0.5 | 0 | 0 | 0 | 200 | 0
Assembled Skid | Testing | 1 | 0 | 0 | 0 | 400 | 0
NDT on Weldings (structure) | Testing | 1 | 0 | 0 | 100 | 400 | 0
Dimensional Check (Structure) | Testing | 0.5 | 0 | 0 | 100 | 200 | 0
Painting Check (Structure) | Testing | 0.5 | 0 | 0 | 100 | 200 | 0
NDT on Weldings (piping) | Testing | 1 | 0 | 0 | 200 | 400 | 0
Dimensional Check (piping) | Testing | 0.5 | 0 | 0 | 200 | 200 | 0
HydroStatic Pressure TEst | Testing | 3 | 0 | 0 | 200 | 1200 | 0
Painting Check (piping) | Testing | 1 | 0 | 0 | 0 | 400 | 0
Observer (Third Party) | Testing | 3 | 0 | 0 | 8000 | 0 | 0
Dimensional Check | Testing | 0.5 | 0 | 0 | 0 | 200 | 0
IECEx Detailed Test | Testing | 3 | 0 | 0 | 0 | 1200 | 0
Automation Test | Testing | 1 | 0 | 0 | 0 | 400 | 0
Final Tests | Testing | 1 | 0 | 0 | 0 | 400 | 0
Documentation Pack | Testing | 2 | 0 | 0 | 0 | 0 | 1120